## INSTRUKTIONER
INDIVIDUELL: Hur gör jag en individuell postmortem? Det är lika viktigt att fundera över sitt eget arbete som gruppens arbete, för att utvärdera hur arbetet lagts upp, hur det har planerats och om planeringen har kunnat hållas. En individuell postmortem är även ett verktyg till utbildarna för att kunna utvärdera om det finns behov av komplettering för att nå betyget godkänt i kursen. Svara på frågorna "Fråga 1-5" Du svarar på frågorna i fliken nedan "Fråga 1-5". Samt fyller i de tasks du jobbat på för varje sprint i respektive sprint flik. Logga tid för varje sprint För att bli bättre på sin tidsestimering så är det viktigt att vi tränar på detta här. Vi vill att ni för varje sprint loggar både planerad/estimerad tidsåtgång samt den faktiska tidsåtgången. Detta gör ni för varje sprint i flikarna nedan. Lämnas in via pingpong Inlämning sker i samband med projektavslutet

## Fråga 1-5
Svara på följande 5 frågor:
1. Hur bedömer jag min egen insats?
Jag anser att min insats har haft en inverkan på projektets slutresultat
2. Efter att ha genomfört Roterande Stolen; vilka är mina reflektioner kring feedbacken jag fick samt feedbacken jag gav?
Vi insåg att vi hade post-mortem kanske lite för tidigt i projektet, så inga frustationer hade hunnit uppstå. Men vi har tagit upp relevanta grejer senare under projektet, samt diskuterat under gruppens post-mortem.
3. Vilka reflektioner har jag kring gruppens insats samt mitt personliga bidrag till gruppdynamiken? Vilka lärdomar tar jag med mig från detta?
Många i gruppen har kunnat bära sin egen vikt i arbete, jag tycker det har fungerat för det mesta, det som inte fungerat har väckts, eller kommer att tas upp inför nästa projekt. Jag anser att jag har kunnat stå på mina egna ben under projektets gång och gjort det jag ska, vilket har bidragit till en slutprodukt. Som projektkoordinator tycker jag även att jag har kunnat styra upp möten ordentligt, men samtidigt gett plats för relevant diskussion. Väldigt generiskt svar men jag är nöjd med min insats.
4. Vilka reflektioner har jag kring den generella processen av att skapa spel och vilka lärdomar tar jag med mig från detta?
Vi inom programmering borde planera vår arbetsfördelning bättre. För mycket arbete har hamnat på enstaka individer i gruppen. Detta är något som lyftes på gruppens post-mortem.
5. Fyll i tasks och tid på övriga flikar (Sprint 1, Sprint 2…)

## Pre-prod 1
Namn: Pontus Fredriksson | Grupp: 6 | Projekt: Spite
Task | Estimerad tid (h) | Faktisk tid (h) | Diff
Planering, möten & backlog | 20 | 20
The engine has been prepared for use | 9 | 12 | 3
There is a way to load levels from UE | 12 | 18 | 6

## Alpha 1
Namn: Pontus Fredriksson | Grupp: 6 | Projekt: Spite
Task | Estimerad tid (h) | Faktisk tid (h) | Diff
Sprintplanning | 3 | 3
There are environmental shadows | 3 | 3
There are spotlight shadows | 3 | 6 | 3
There are pointlight shadows | 6 | 6
The engine has been refactored | 9 | 6 | -3
There is a particle system implemented | 6 | 3 | -3
There is support for debugdrawing | 3 | 3
There is support for deferred rendering | 12 | 15 | 3
There is a navmesh load system | 6 | 6

## Alpha 2
Namn: Pontus Fredriksson | Grupp: 6 | Projekt: Spite
Task | Estimerad tid (h) | Faktisk tid (h) | Diff
Sprintplanning | 3 | 3
Animations are implemented in the engine | 15 | 19 | 4
There is a boss existing in a level | 2 | 3 | 1
There is debris circulating the boss arena | 2 | 3 | 1
The boss can clam into the ground | 4 | 1 | -3
The boss can swipe the platform | 4 | 3 | -1
There are occasionally falling debris landing on the boss platform | 4 | 4
The boss can screech and slow the player movement | 4 | 1 | -3
Spelaren upplever att det är bra flow på navigeringen | 8 | 8

## Beta 1
Namn: Pontus Fredriksson | Grupp: 6 | Projekt: Spite
Task | Estimerad tid (h) | Faktisk tid (h) | Diff
The player experiences a correctly placed and rotated camera | 4 | 1 | -3
Ability 1 - Spelaren kan dra in fiender | 6 | 6
Ability 3 - Spelaren kan skjuta iväg en sten mesh | 7 | 2 | -5
Spelaren kan attackera fiender | 2
Spelaren kan ta skada | 2
Spelaren kan dö och återuppstå (respawn) | 2
Spelaren kan plocka upp health globes som återställer health | 2
Spelaren upplever en animation när man interagerar med ett objekt. | 1
Spelaren upplever en run animation när man rör på sig. | 1 | 1
Spelaren upplever en idle animation när man står still. | 1 | 1
Spelaren upplever en death animation när man dör. | 1 | 1
LMB - Spelaren kan exekvera en 3-stegs kombo (Jab, kick, sweep). | 5 | 1 | 4
Ability 2 - Spelaren kan göra skada i en cirkel runtom sig. | 5 | 3 | 2
Ability 4 - Spelaren kan använda sin ultimate ability. | 5 | 3 | 2
Spelarens Hastighet stämmer överens med metrics i Diablo 3. | 1 | 1
Spelaren upplever en kamera med rätt avstånd, låst till spelaren i relation till Diablo 3. | 1 | 1

## Beta 2
Namn: Pontus Fredriksson | Grupp: 6 | Projekt: Spite
Task | Estimerad tid (h) | Faktisk tid (h) | Diff
The player uses string pulling | 10 | 10
The boss has animations | 2 | 3 | 1
The boss has replaced debug draws with meshes | 3 | 3
There is a system for emitting explosive particles | 3 | 3
There is screen shake | 2 | 3 | 1
The boss can knockback the player | 2 | 2
The player can dash a short distance with attacks | 2 | 2
There is damage numbers | 3 | 3
There are climbing enemies during the boss fight | 2 | 4 | 2
There are VFX on boss landing debris attack | 2 | 1 | -1
There is a boss event for phase 1 | 3 | 3
There is a boss phase 3 intro | 3 | 3
The boss swipe attack uses OBB instead of sphere collision | 3 | 3

## Polish
Namn: Pontus Fredriksson | Grupp: 6 | Projekt: Spite
Task | Estimerad tid (h) | Faktisk tid (h) | Diff
The boss can swipe in both directions | 3 | 3
The player has passive regen | 2 | 2
There are visual cooldowns on abilities | 1 | 2 | 1
There is an ingame main menu | 6 | 6
There are game states that saves player progress | 3 | 3
There is VFX, particles and light for player ultimate | 4 | 4
There are correctly timed VFXes for the boss | 7 | 7
There is a brazier prefab with particles/light | 2 | 2
There is a guide in the hub | 5 | 5
There is a prefab using custum pixel shader for health orbs | 1 | 1
The cinematics have all been implemented at the correct place | 2 | 3 | 1
There is a polished version of boss phase 1 event | 2 | 2
The holy ground aura ability have been reworked | 2 | 3 | 1
There is a threaded loading screen | 4 | 4
The player can die, respawn and restart the level | 2 | 2
The player chasm ability does not go further than the navmesh | 1 | 2 | 1
There is snow falling at level 2 | 1 | 1
The enemies have sound effects | 2 | 1 | -1
The boomer explosion effect has been polished | 2 | 2
Spelaren rycker inte längre i sina animationer | 1 | 3 | 2
Spelaren låser upp sina abilities korrekt | 1 | 1
Spelarens statemachine har blivit uppstädad på skräpkod | 2 | 2
There is a globe for resource | 1 | 1
There is a visual portal for the levels unlocked | 2 | 3 | 1
There is telegraphing for boomer explosion | 1 | 1
The boomer deals damage to enemies | 1 | 1
There is a highlight effect in the menues | 2 | 1 | -1
There are randomly cllimbing enemies in the levels | 2 | 1 | -1
Fixade 2 krashningar (A-bugar) | 1 | 1
There is animation cancelling for more responsive combat | 2 | 2

## Inlämningsvecka
Namn: Pontus Fredriksson | Grupp: 6 | Projekt: Spite
Task | Estimerad tid (h) | Faktisk tid (h) | Diff
Level select har blivit polished | 4 | 4
Buggfix | 15 | 15
Fade mellan cinematics | 1 | 1
Spelaren kan trampa på råttor | 3 | 2 | -1
The player dash has been polished | 3 | 3
The player combo attack has VFX | 1 | 1
The player can unlock a secret level | 3 | 3
The player can dance | 1 | 1
The rats can dance when the player dances | 1 | 1
The boss environment shader has correct colors | 2 | 2
Rensa skräpfiler och förbereda inlämning | 1 | 1
Grupp post-mortem | 3 | 3
Progg specifik grupp post-mortem | 3 | 3
Trailer, screenshots & individuella post-mortem | 8 | 8